**Harvey High School IMPROVEMENT PLAN French**



**2019-2020**

**Data Snapshot Summary:**

**Goal: To enrich and promote bilingualism within the classroom and school setting.**

**Indicators of Success:** Students will be aware of opportunities to use their second language skills.

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **STRATEGIES/ACTIONS** | **IMPLEMENTATION PLAN** | | **MONITORING PLAN** | | | **MONITORING UPDATES** | |
| **Strategy/Action** | **Responsibility** | **Timeframe** | **Evidence** | **Accountability** | **Frequency** | **Impact** | **Next Steps** |
| *(List the strategies and actions for realizing this goal, each in a new row.)* | *(Who is implementing this strategy/action?)* | *(In what timeframe/date range will implementation occur?)* | *(What evidence will be examined?)* | *(Who is examining the evidence?)* | *(At what frequency will the evidence be examined?)* | *(What has been the impact of this strategy/action toward achievement of the goal?)* |  |
| FSL teachers will apply for a grant to enrich and promote bilingualism at HHS.  Grant approved | FSL teachers will discuss together and Tina will submit the application.  Tina | Prior to Oct. 25 and must be sent to Janice Gagnon  Submitted 10/11/19 and approval received | Approval of grant  Grant funds received | FSL Teachers |  |  | embedded  continue  refine or revise  abandon  not yet implemented |
| Calithumpians to be invited to perform a bilingual piece to all students and hold a workshop for 12 FI Theatre Arts Class | Tina to arrange and David to greet the crew when they arrive. | Nov. 27th | Performance and workshop held. 12 FI Theatre Arts class provided their reflections on the workshop. | FSL PLC group |  | Student reflections received but need to be shared with French PLC | embedded  continue  refine or revise  abandon  not yet implemented |
| Presentations by the Office of the Commissioner of Official Languages of Canada | Tina to arrange for Grades 7 and 8 FI students | March 19th in the morning for 7 & 8 FI | Feedback from students |  |  |  | embedded  continue  refine or revise  abandon  not yet implemented |
| FSL teachers will incorporate “News in Slow French” into their lessons. 4 Licenses to be purchased. | FSL teachers to use this resource. Andrea will look after placing the order online.  Order placed by  Andrea | November/December  November 14, 2019 | *Grade 11/12 FILA Class using News in Slow French as Oral Comprehension practice and to start discussions of current events (OPI prep). First activity shows high degree of understanding of “Advanced” audio.* | *David FILA 11/12* | *Weekly activity* |  | embedded  continue  refine or revise  abandon  not yet implemented |